## Timesheet
WEEK 09 - 23 Feb to 28 Feb 2026
Name: Joe
Please provide the Client / Project Name & Address and the Work Description you completed for that Client
| From: | 16/02/2026 | To: | 21/02/2026 |  |  |  |  | Licence No 292303c
Dates: Week Ending 21 Feb 2026 | [8 empty] | accounts@lfcs.com.au
admin@lfcs.com.au
Day | Date | Start Time | Finish Time | Lunch Duration | Total Hours Worked | Client / Project Name & Address |  | Work Description |  | Day Works Y / N |  | Approval Signature
Mon | 16/02/2026 |  |  |  | 12 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Strip & clean formwork from previous pour. Set out new wall kickers. Steel fixing to lift core walls. |  |  | Y N
Tue | 17/02/2026 |  |  |  | 10 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Formwork erection to core walls. Plumb & brace panels. Install cast-in items. |  |  | Y N
Wed | 18/02/2026 |  |  |  | 10 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Complete steel fixing to core walls. Tie-off starter bars. Pour prep & concrete pour. |  |  | Y N
Thur | 19/02/2026 |  |  |  | 10 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Strip core wall formwork. Cure & patch. Begin set out for ground beams. |  |  | Y N
Fri | 20/02/2026 |  |  |  | 8 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Steel fixing to ground beams. Form edges & kickers. General site clean-up. |  |  | Y N
Sat | 21/02/2026 |  |  |  | 9 | Ford Civil Powerhouse Museum Parramatta 69 Phillip St, Parramatta |  | Formwork to ground beams. Box outs & penetrations. Pour prep for Monday. |  |  | Y N
Sun | [10 empty] | Y N
Total Hours Worked
Signature: |  |  |  | Date: |  |  | Approval Signature: