## Timesheet
LF CONSTRUCTION SERVICES TIMESHEET
Name: Michael McLoughlin
Please provide the Client / Project Name & Address and the Work Description you completed for that Client
| From: |  | To: | [5 empty] | Licence No 292303c
Dates: 9 Feb - 15 Feb 2026 | [8 empty] | accounts@lfcs.com.au
admin@lfcs.com.au
Day | Date | Start Time | Finish Time | Lunch Duration | Total Hours Worked | Client / Project Name & Address |  | Work Description |  | Day Works Y / N |  | Approval Signature
Mon | 9 Feb | - | - | - | 8 | LF Construction Services |  | Take out of hours owed |  | N | Y N
Tue | 10 Feb | - | - | - | 8 | LF Construction Services |  | Take out of hours owed |  | N | Y N
Wed | 11 Feb | 7:00 AM | 3:00 PM | 30 min | 7.5 | Ford Civil - Parramatta Powerhouse |  | Edge board (curved section), heights set between pylons, formwork |  | Y | Y N
Thur | 12 Feb | 7:00 AM | 4:30 PM | None | 9.5 | Ford Civil - Parramatta Powerhouse |  | Edge boards, pit box-out, mesh installed, concrete pour |  | Y | Y N
Fri | 13 Feb | 7:00 AM | 4:30 PM | None | 9.5 | Ford Civil - Parramatta Powerhouse |  | Steel stop ends, Z-bars, control joints, expansion joints, concrete poured |  | Y | Y N
Sat | 14 Feb | 7:00 AM | 3:00 PM | None | 8 | Ford Civil - Parramatta Powerhouse |  | Edge board, control joints, bitumen board, stop ends |  | Y | Y N
Sun | [10 empty] | Y N
Total Hours Worked
Signature: |  |  |  | Date: |  |  | Approval Signature: